## Sheet1
STATUS | PRIORITY | DEADLINE | TASK | DESCRIPTION | ASSIGNED TO | DELIVERABLE | % DONE | FIXED COST | ESTIMATED HOURS | ACTUAL HOURS | STATUS KEY | PRIORITY KEY
|  |  | Web Application | [7 empty] | Not Started | High
Complete | High | 2021-02-07 | Plan out rough design | A rough design that both of us can easily follow and use as a basis for creating the project | Both | A few sketches(wireframe will more or less be the deliverable) | 100% |  | 1-2 hours | 1 hour | In Progress | Medium
Complete | High | 2021-02-05 | Write up Progress week 1 | Documenting the progress we have taken in the first week. | Ciaran | Week 1 document | 100% |  | 1-2 hours | 1 hour | In Progress | Medium
In Progress | High | 2021-05-07 | Create a wireframe for design | Design that has been advanced upon and advisises a clear vision | Milosz | Wireframe deliverable | 30% |  | 1-3 hours |  | Complete | Low
Overdue | High | 2021-02-07 | Set up GitHub | Where all the work will be submitted and held | Either | Github link | 0% |  | 10 mins |  | Complete | Low
On Hold | Low | 2021-02-21 | Create a suitable database (mongo) | Use of storage on the web application | (decide later) | Mongodb database | 0% |  | 30 mins |  | On Hold
Not Started | Medium | 2021-02-07 | Set up individual work environments | So both members can work on all aspects of the project. (probably have most tools installed already) | Both | Working machines | 0% |  | Variable |  | Overdue
Not Started | High | 2021-03-30 | Start Developing the back end | The front end of the project, what the user will see. Design and structure of this | Both | The application itself, the web pages | 0% |  | Over a few weeks (varies)
Not Started | High | 2021-03-11 | Start front end development | The back end, used for get requests, connections to database etc | Both | The application itself, the server etc | 0% |  | Over a few weeks (varies)